## Slide 1: Action Plans
CARNA Regional Planning Ad Hoc Committee
212th RSC – December 2021

## Slide 2: How did we get here?
October two-day 2020 – Group Conscience to have another planning cycle
Regional Planning Survey developed based on feedback and past survery, sent out in September
October two-day 2021: Planning Survey results presented and approaches developed
Approaches with the highest votes–> Action Plans

## Slide 3: What are the components of an Action Plan?
What Task needs to be done?
When do these task need to be accomplished?
Who are the trusted servants that will be responsible?
Identification of individual points of accountability to track progress?
How much time and money?

## Slide 4: Which approaches got the most votes?
Encouraging service outreach / Making Service Attractive
Communicating Accomplishments and Goals / Announcing Sub-committee projects
Encouraging GSR Assembly Participation
Mentorship
One Page Info Sheet Given to Areas (need direction)

## Slide 5: Encouraging Service Outreach / Making Service Attractive
What Task needs to be done: Workshop ideas for an action plan during the April two-day, then asking the Chairperson to create an ad hoc to put them into motion
When these task need to be accomplished: Aprill two-day
Who are the trusted servants that will be responsible: Regional Delegate team, then the Chairperson
Points of accountability: RD Team / Chair
How much time and money: no impact on RSC, just the time for the trusted servants

## Slide 6: Communicating Accomplish & Goals / Announcing Projects
What Task needs to be done: To be discussed today in Open Forum
When these task need to be accomplished: TBD
Who are the trusted servants that will be responsible: TBD
Points of accountability: TBD (Policy?)
How much time and money: No Impact

## Slide 7: Encouraging Participation in the GSR Assembly
What Task needs to be done: Creation of a webpage on the CARNA website followed by mass email & encouraging RCMs to spread the word
When these task need to be accomplished: ASAP
Who are the trusted servants that will be responsible: RD Team
Points of accountability: RD Team and webservant
How much time and money: No money, moderate time commitment

## Slide 8: Mentorship in Service
What Task needs to be done: Workshop on Mentorship to generate ideas around how to implement mentorship
When these task need to be accomplished: October two-day
Who are the trusted servants that will be responsible: RD team to lead workshop
Points of accountability: RD team for now
How much time and money: No money, time at two-day

## Slide 9: One Page Info Sheet Given to Areas
What Task needs to be done: Create a one-page hand out that RCMs can take to their Areas to explain concisely what the Region is and what it does
When these task need to be accomplished: ASAP. This item is the only holdover from the last planning cycle
Who are the trusted servants that will be responsible: Chairperson to direct the elected officer to write a brief description on what they do
Points of accountability: Chairperson
How much time and money: No money, moderate time

## Slide 10: Thank you for allowing us to serve!
-Your Regional Planning Ad Hoc Committee